## Sayfa2
Milestone | Start Date | End Date | Task | Effort (Hours)
Week 1 | 2020-10-28 08:00 | 2020-11-03 17:00 | Research on Wikidata | 3
|  |  | Modify ReadMe | 1
|  |  | Setup VS Code Connection | 1
Week 2 | 2020-11-04 08:00 | 2020-11-10 17:00 | Prepare Questions For Requirement Elicitation | 2
Week 2 |  |  | Research on git | 1
Week 3 | 2020-11-11 08:00 | 2020-11-17 17:00 | Create Mockup | 2
Week 4 | 2020-11-18 08:00 | 2020-11-24 17:00 | Finalize SRS | 1
|  |  | Test Twitter API | 4
Week 5 | 2020-11-25 08:00 | 2020-12-01 17:00 | Django Research | 6
|  |  | Start Project Planning Document | 3
|  |  | Test MongoDB | 3
Week 6 | 2020-12-02 08:00 | 2020-12-08 17:00 | Dockerize the Django Application | 4
|  |  | Research On PostgreSQL | 2
|  |  | Test Entity Linking Via TagMe | 2
|  |  | Find A Method For Sentiment Analysis | 4
Week 7 | 2020-12-09 08:00 | 2020-12-15 17:00 | Perform Sentiment Analysis On Cleaned Data | 4
|  |  | Implement Data Cleaning | 5
|  |  | Decide on Data Cleaning Strategy | 3
|  |  | Schedule A Job For Routine Data Collection | 4
|  |  | Create a Table At DB to Store Twitter Data | 1
|  |  | Store Analyzed Stream Data at DB | 5
|  |  | Switch (on Dockerized) Application From SqlLite to PostGreSQL | 1
Week 8 | 2020-12-16 08:00 | 2020-12-22 17:00 | Find and Implement a Bootstrap Theme | 4
|  |  | Create Sign Up Page | 5
|  |  | Create the Login Page | 2
|  |  | Create a Welcome / Opening Page for Application | 2
Week 9 | 2020-12-23 08:00 | 2020-12-29 17:00 | Create the Sidebar | 1
Week 10 | 2020-12-30 08:00 | 2021-01-05 17:00 | Set up "Search in time" page | 4
|  |  | Set up "Search words" page | 4
Week 11 | 2021-01-06 08:00 | 2021-01-12 17:00 | Create Postgres DB on Heroku | 3
|  |  | Deploy to Prod using Heroku | 4
|  |  | Configure Environment Variables on Heroku | 1
|  |  | Create .env File | 1
|  |  | Deploy docker app to cloud. | 36
Week 12 | 2021-01-13 08:00 | 2021-01-19 17:00 | snscrape Does Not Work on Heroku - find alternative | 8
Write The Documentation For the Application
Finalize Overall Tests of The Application
|  |  | Test User Login/Log Out To Website | 5
|  |  | Create Concurrency Network | 6
|  |  | Re-evaluate Necessity of Account Page | 2
|  |  | Create This Week Page | 7
|  |  | Organize Date Search Results Page | 2
|  |  | Transfer data on local db to Prod DB | 8
|  |  | Schedule Data Collection Job on Heroku | 2